## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a developer, I want to design and create SQLite database schema for storing crypto prices and portfolio metadata. | Must Have | None | Hariom | Completed
Sprint 1 | Sprint 1 | US02 | As a developer, I want to load BTC & ETH historical price data from CSV files into SQLite using pandas. | Must Have | Database schema | Hariom | Completed
Sprint 1 | Sprint 1 | US03 | As a developer, I want to calculate daily returns and cumulative returns for assets. | Must Have | Price data loaded | Hariom | Completed
Sprint 1 | Sprint 1 | US04 | As a developer, I want to calculate portfolio expected return and risk using asset weights. | Must Have | Daily returns | Hariom | Completed
Sprint 2 | Sprint 2 | US05 | As a developer, I want to implement insertion of portfolio metrics into relational tables. | Must Have | Metrics calculation | Hariom | Completed
Sprint 2 | Sprint 2 | US06 | As a developer, I want to ensure transactions commit properly for data consistency. | Must Have | DB design | Hariom | Completed
Sprint 2 | Sprint 2 | US07 | As a developer, I want to create functions for Risk-Based and Goal-Based allocation strategies. | Must Have | Metrics completed | Hariom | Completed
Sprint 2 | Sprint 2 | US08 | As a developer, I want to implement ThreadPoolExecutor for parallel execution of strategies. | Must Have | Strategy functions | Hariom | Completed
Sprint 2 | Sprint 2 | US09 | As a developer, I want to simulate BTC & ETH random walk data for portfolio testing. | Must Have | Python numpy | Hariom | Completed
Sprint 2 | Sprint 2 | US10 | As a developer, I want to calculate and visualize cumulative portfolio vs single asset returns. | Must Have | Simulated data | Hariom | Completed
Sprint 3 | Sprint 3 | US11 | As a developer, I want to implement 6 risk check functions (Volatility, Sharpe, Sortino, Beta, Drawdown, Max Weight). | Must Have | Portfolio returns | Hariom | Completed
Sprint 3 | Sprint 3 | US12 | As a developer, I want to design risk_assessment table in SQLite for storing results. | Must Have | Risk functions | Hariom | Completed
Sprint 3 | Sprint 3 | US13 | As a developer, I want to integrate Gmail SMTP alerts for failed risk rules. | Must Have | Risk results | Hariom | Completed
Sprint 3 | Sprint 3 | US14 | As a developer, I want to build predictor module using Linear Regression to forecast returns. | Must Have | Cleaned returns | Hariom | Completed
Sprint 3 | Sprint 3 | US15 | As a developer, I want to evaluate predictive model using MSE and R² metrics. | Must Have | Predictor module | Hariom | Completed
Sprint 3 | Sprint 3 | US16 | As a developer, I want to store predictions and evaluation metrics into SQLite. | Must Have | Model training | Hariom | Completed
Sprint 4 | Sprint 4 | US17 | As a developer, I want to implement rule-based allocation (Equal-Weight, Risk-Parity, Sharpe, Momentum). | Must Have | Portfolio data | Hariom | Completed
Sprint 4 | Sprint 4 | US18 | As a developer, I want to simulate Bull, Bear, and Volatile market conditions for stress testing. | Must Have | Allocation rules | Hariom | Completed
Sprint 4 | Sprint 4 | US19 | As a developer, I want to analyze rule performance under stress and store results in Stress_Test.db. | Must Have | Stress test scenarios | Hariom | Completed
Sprint 4 | Sprint 4 | US20 | As a developer, I want to generate summary report of all phases (M2 → M4) for project submission. | Must Have | All modules completed | Hariom | Completed
Sprint 4 |  | US21
US22
US23
US24
US25
US26
US27
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 64 | 3 | 2 | 4 | 5 | 7 | 4 | 5 | 6 | 5 | 5 | 6 | 4 | 3 | 5
SPRINT 1 BACKLOG
US-001 | T-001.1 | Install core IDE (VS Code/PyCharm) and Git. | 2025-08-10 | 2025-08-10 | Hariom | Setup | Done | 1 | bar: Day 1
US-001 | T-001.2 | Initialize project repository and commit initial file structure. | 2025-08-10 | 2025-08-11 | Hariom | Setup | Done | 3 | Day 1: 2; Day 2: 1
US-001 | T-001.3 | Create and configure Python Virtual Environment. | 2025-08-11 | 2025-08-11 | Hariom | Setup | Done | 1 | bar: Day 2
US-001 | T-001.4 | Install initial dependencies: Pandas, NumPy, SQLite3. | 2025-08-12 | 2025-08-12 | Hariom | Requirements | Done | 3 | Day 3: 3
US-002 | T-002.1 | Define Primary User Roles (e.g., Registered User, Admin, System). | 2025-08-12 | 2025-08-13 | Hariom | Requirements | Done | 4 | Day 3: 1; Day 4: 3
US-002 | T-002.2 | Draft Initial User Stories for authentication (Login, Signup). | 2025-08-13 | 2025-08-14 | Hariom | Requirements | Done | 5 | Day 4: 2; Day 5: 3
US-002 | T-002.3 | Draft Initial User Stories for data viewing (View Balance, View History). | 2025-08-14 | 2025-08-14 | Hariom | Data Acquisition | Done | 4 | Day 5: 4
US-002 | T-002.4 | Apply MOSCOW prioritization to the initial 10 User Stories. | 2025-08-15 | 2025-08-15 | Hariom | Data Acquisition | Done | 4 | Day 6: 4
US-003 | T-003.1 | Research and acquire historical BTC price data (CSV format). | 2025-08-16 | 2025-08-16 | Hariom | Data Prep | Done | 5 | Day 7: 5
US-003 | T-003.2 | Research and acquire historical ETH price data (CSV format). | 2025-08-17 | 2025-08-17 | Hariom | Data Prep | Done | 6 | Day 8: 6
US-003 | T-003.3 | Inspect raw CSV files: identify columns, date format, and required cleaning steps. | 2025-08-18 | 2025-08-18 | Hariom | Data Prep | Done | 5 | Day 9: 5
US-004 | T-004.1 | Define High-Level System Architecture (Python/Pandas → SQLite DB). | 2025-08-19 | 2025-08-19 | Hariom | Architecture | Done | 4 | Day 10: 4
US-004 | T-004.2 | Sketch Database Entity Relationship Diagram (ERD) for core tables. | 2025-08-19 | 2025-08-20 | Hariom | Design | Done | 5 | Day 10: 1; Day 11: 4
US-004 | T-004.3 | Define a set of Non-Functional Requirements (e.g., Security, Performance goals). | 2025-08-20 | 2025-08-21 | Hariom | Planning | Done | 6 | Day 11: 2; Day 12: 4
US-001 to 004 | T-005.1 | Review and finalize Project Scope and Definition of Done (DoD) for M1. | 2025-08-22 | 2025-08-22 | Hariom | Planning | Done | 3 | Day 13: 3
US-001 to 004 | T-005.2 | Prepare the final Milestone 1 Report draft. | 2025-08-23 | 2025-08-23 | Hariom | Documentation | Done | 5 | Day 14: 5
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 (M1) | 10 Aug – 23 Aug
| 2025-08-14 | Difficulty acquiring clean, time-aligned historical CSV data for both BTC and ETH. | Switched from a primary source to a pre-formatted Kaggle dataset; applied Pandas ffill() for minor missing values.
| 2025-08-18 | Ambiguity in defining the 'System' user role for initial user stories. | Held a brief consultation (Scrum Master/Mentor) to clarify that 'System' represents automated jobs (DB insertions, API calls).
| 2025-08-22 | Delay in finalizing the high-level DB schema due to unexpected complexity in asset allocation tables. | Simplified the schema initially by consolidating allocation logic into one portfolio_assets table for M1/M2.
S2 (M2) | 24 Aug – 6 Sep
| 2025-08-28 | Error in Portfolio Risk calculation due to incorrect matrix multiplication (covariance vs. weights). | Pair-programmed the core matrix logic with a team member and verified the formula against standard financial literature.
| 2025-09-01 | Python ThreadPoolExecutor (M2P3) resulted in unexpected resource consumption during concurrent runs. | Adjusted the maximum number of worker threads to match the available CPU cores to stabilize execution.
| 2025-09-05 | Challenges in accurately simulating realistic cumulative return data for M2P4 (Random Walk technique). | Reset random seed and iterated the simulation parameters to ensure the results demonstrated expected financial characteristics (i.e., high crypto volatility).
S3 (M3) | 7 Sep – 20 Sep
| 2025-09-10 | Beta calculation was initially flawed because market returns were not time-aligned with portfolio returns. | Filtered both return series by the common timestamp index before calculating covariance (resolved in Risk_checker.py).
| 2025-09-14 | Linear Regression model (M3P2) showed poor R2 scores, suggesting limited predictive power for crypto returns. | Documented the finding in the report, emphasizing that the model serves as a baseline and recommended future use of advanced models (e.g., XGBoost).
| 2025-09-17 | Gmail SMTP connection failure due to security settings preventing external application login (M3P1). | Updated the SENDER_PASSWORD to a specific App Password generated within Google Account Security settings.
S4 (M4) | 21 Sep – 4 Oct
| 2025-09-24 | Difficulty in mathematically isolating the logic for the Sharpe-Maximization and Momentum allocation rules. | Broke down T-302.1 into smaller tasks; focused on isolating the metric calculation (Sharpe, Momentum signal) before applying the weighting logic.
| 2025-09-27 | Stress Testing (M4P1) failed to clearly distinguish portfolio behavior under different scenarios due to synthetic data being too similar. | Adjusted the magnitude of return shocks (positive/negative percentages) in Bull and Bear scenarios to exaggerate market behavior for clearer results.
| 2025-10-03 | Final integration test failed because the Stress_Test.db was not accessible by the main Python environment. | Standardized all database file paths to use relative references and ensured the DB was initialized before insertion (resolved file access issues).

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 (M1) - Foundation | 2025-08-10 | 2025-08-23 | Hariom |  |  |  | Action taken
2 | 1 | 2025-08-10 | 2025-08-23 | Hariom | (Process) Creating specific task checklists for data cleaning steps before starting coding. | (Technical) Using hardcoded file paths that cause issues for teammates. | (Technical) Using hardcoded file paths that cause issues for teammates.
3 | 2 | 2025-08-10 | 2025-08-23 | Hariom | (Technical) Implementing minimal error handling (try/except) for DB connection attempts. | (Process) Leaving User Stories vague; ensuring Acceptance Criteria are clearly defined before development starts. | (Process) Leaving User Stories vague; ensuring Acceptance Criteria are clearly defined before development starts. | Standardized all file paths to relative paths in the code base.
4 | 3 | 2025-08-10 | 2025-08-23 | Hariom | (Collaboration) Utilizing the daily standup time strictly for status updates and identifying roadblocks. | (Process) Allowing distractions from other projects during focused coding blocks. | (Process) Allowing distractions from other projects during focused coding blocks. | Held a session to define clear Acceptance Criteria for core metrics calculation.
5 | 4 | 2025-08-10 | 2025-08-23 | Hariom | (Technical) Creating dedicated modules for DB functions separate from calculation logic. | (Collaboration) Waiting until the sprint review to address technical conflicts in code merge. | (Collaboration) Waiting until the sprint review to address technical conflicts in code merge. | Instituted a 1-hour "Deep Work" block daily, free from communication.
6 | S2 (M2) - Metrics/Parallelism | 2025-08-24 | 2025-09-06 | Hariom |  |  |  | Created a dedicated db_utils.py file for all database interactions.
7 | 5 | 2025-08-24 | 2025-09-06 | Hariom | (Process) Reviewing the definition of complex metrics (e.g., Sharpe, Sortino) before coding the function. | (Technical) Using inefficient loops for cumulative calculations (e.g., Max Drawdown). | (Technical) Using inefficient loops for cumulative calculations (e.g., Max Drawdown).
8 | 6 | 2025-08-24 | 2025-09-06 | Hariom | (Technical) Implementing basic logging to track successful and failed metric calculations in the console. | (Collaboration) Attempting to debug blocking issues for more than 45 minutes alone. | (Collaboration) Attempting to debug blocking issues for more than 45 minutes alone. | Dedicated time to refactoring Max Drawdown calculation using cumulative max techniques.
9 | 7 | 2025-08-24 | 2025-09-06 | Hariom | (Process) Adding time estimates for documentation tasks (e.g., README updates) directly to the backlog. | (Technical) Failing to check for zero division errors in ratio calculations (Sharpe, Sortino). | (Technical) Failing to check for zero division errors in ratio calculations (Sharpe, Sortino). | Introduced the "30-minute rule" to enforce seeking immediate help for blockers.
10 | S3 (M3) - Risk & Prediction | 2025-09-07 | 2025-09-20 | Hariom |  |  |  | Added specific checks (if std == 0: return 0.0) to ratio functions to prevent runtime errors.
11 | 8 | 2025-09-07 | 2025-09-20 | Hariom | (Technical) Implementing unit tests specifically for the risk threshold comparison logic (PASS/FAIL). | (Collaboration) Assuming the API Key/SMTP setup worked without external end-to-end testing. | (Collaboration) Assuming the API Key/SMTP setup worked without external end-to-end testing.
12 | 9 | 2025-09-07 | 2025-09-20 | Hariom | (Process) Using the "Actual Effort" column to log time accurately against original estimates. | (Technical) Hardcoding risk thresholds into the function instead of using the global RISK_THRESHOLDS config. | (Technical) Hardcoding risk thresholds into the function instead of using the global RISK_THRESHOLDS config. | Created a sandbox script to separately verify email sending functionality before integration.
13 | 10 | 2025-09-07 | 2025-09-20 | Hariom | (Technical) Ensuring data integrity by implementing a check to see if DB insertion succeeded before logging success. | (Collaboration) Allowing a gap between code completion and submitting the code for peer review. | (Collaboration) Allowing a gap between code completion and submitting the code for peer review. | Moved all threshold values into the centralized configuration dictionary.
14 | S4 (M4) - Strategy & Finalization | 2025-09-21 | 2025-10-04 | Hariom |  |  |  | Implemented a check on the cursor.rowcount after DB insertion to verify success.
15 | 11 | 2025-09-21 | 2025-10-04 | Hariom | (Process) Breaking down the Final Report/Presentation creation into smaller, scheduled tasks. | (Technical) Using multiple, inconsistent data preparation functions for historical vs. synthetic data. | (Technical) Using multiple, inconsistent data preparation functions for historical vs. synthetic data.
16 | 12 | 2025-09-21 | 2025-10-04 | Hariom | (Technical) Standardizing all rule allocation outputs (weights) into a consistent Pandas Series/JSON format for DB storage. | (Process) Starting documentation late in the milestone, causing a rush at the end. | (Process) Starting documentation late in the milestone, causing a rush at the end. | Consolidated data preparation logic into one parameterized function for flexibility.
17 | 13 | 2025-09-21 | 2025-10-04 | Hariom | (Process) Conducting a final, comprehensive system integration test covering M1 through M4 dependencies. | (Technical) Writing verbose code for strategic rules when concise mathematical formulas could be used. | (Technical) Writing verbose code for strategic rules when concise mathematical formulas could be used. | Started the Final Report draft as soon as M4 development began.
18
19