## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
S1 (10 Aug - 23 Aug): Foundation | [9 empty] | Remarks
1 |  | 2025-08-14 | Raw CSV data contained dates in 'dd-mm-yyyy' format, causing Pandas read_csv to fail on index creation. | S1 |  | Data | Explicitly passed parse_dates=True and dayfirst=True flags during loading. | 2025-08-14 | Closed
2 |  | 2025-08-16 | Portfolio Risk function produced a NaN result when attempting to calculate the covariance matrix. | S1 |  | Calculation | Ensured that both asset return series were merged and time-aligned before calculation (resolved missing index values). | 2025-08-17 | Closed | Initial data load successful.
3 |  | 2025-08-19 | DB connection was not being properly closed, leading to resource locks on the SQLite file during subsequent runs. | S1 |  | Technical | Refactored the connection logic to use Python's with sqlite3.connect(...) as conn: pattern for auto-closing. | 2025-08-20 | Closed | Risk calculation is now stable.
4 |  | 2025-08-21 | The portfolio_assets table was created without a foreign key, breaking the relational integrity check. | S1 |  | Database | Dropped and recreated the table schema to include a Foreign Key link to the portfolio table ID. | 2025-08-22 | Closed | Resources correctly managed.
S2 (24 Aug - 6 Sep): Core Metrics | [9 empty] | Schema integrity restored.
5 |  | 2025-08-27 | The Sharpe Ratio function raised a ZeroDivisionError when portfolio returns had zero standard deviation over a short period. | S2 |  | Calculation | Added a conditional check: if std == 0: return 0.0 to handle edge case gracefully. | 2025-08-28 | Closed
6 |  | 2025-08-30 | Max Drawdown calculation failed to find the true peak-to-trough decline due to incorrect indexing of cumulative returns. | S2 |  | Logic | Refined the logic to use .cummax() on cumulative returns to accurately track the peak value. | 2025-08-31 | Closed | Added error handling for stable ratio calculation.
7 |  | 2025-09-03 | Beta calculation function produced an inflated result because it used the variance of raw returns instead of daily changes. | S2 |  | Calculation | Corrected the input to ensure only percentage daily return series were used for covariance and variance. | 2025-09-04 | Closed | Drawdown calculation verified against known figures.
S3 (7 Sep - 20 Sep): Risk & Prediction | [9 empty] | Beta now correctly reflects market sensitivity.
8 |  | 2025-09-10 | The Risk Threshold Check function (PASS/FAIL) incorrectly used a strict equality check (e.g., < 1.0) instead of including the threshold (<= 1.0). | S3 |  | Logic | Updated the risk checking engine to use the predefined operator string and boundary conditions consistently. | 2025-09-11 | Closed
9 |  | 2025-09-13 | Email alert system failed to send emails after deployment due to an external security restriction. | S3 |  | Configuration | Changed the SENDER_PASSWORD to an App Password specific to the SMTP login process. | 2025-09-14 | Closed | Threshold checks now include the boundary value.
10 |  | 2025-09-16 | The Prediction DB storage created duplicate summary entries (predictions table) on every script run. | S3 |  | Database | Implemented a DELETE command before insertion to clear old predictions for the current run's portfolio name. | 2025-09-17 | Closed | Alerting functionality confirmed.
11 |  | 2025-09-18 | The Linear Regression model (M3P2) showed poor performance (negative R-squared value). | S3 |  | Model | Documented the finding as a known limitation of using linear models on crypto returns, setting correct expectations. | 2025-09-19 | Closed | Ensures only the latest prediction run is stored.
S4 (21 Sep - 4 Oct): Strategy & Testing | [9 empty] | Defect acknowledged and documented in the report.
12 |  | 2025-09-24 | The Momentum Rule returned zero weights for both assets, resulting in a ZeroDivisionError during normalization. | S4 |  | Logic | Added a fallback check: if momentum_weights.sum() == 0 then assign Equal Weights to prevent failure. | 2025-09-25 | Closed
13 |  | 2025-09-27 | The Stress Test DB (Stress_Test.db) was not initializing correctly because weights were inserted as Python dictionaries. | S4 |  | Database | Modified insertion logic to serialize weights using weights.to_json() before storing in the TEXT column. | 2025-09-28 | Closed | Momentum logic is now robust against flat periods.
14 |  | 2025-09-30 | Risk-Parity Rule logic produced inconsistent weights when data contained very low volatility figures near zero. | S4 |  | Calculation | Implemented a small constant epsilon in the inverse volatility calculation to handle near-zero standard deviations. | 2025-10-01 | Closed | Weights are successfully stored as serializable strings.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others